## roadmap
Roadmap
Version 1.0
Name | Subitems | Epic Owner | Description | Planned Timeline - Start | Planned Timeline - End | monday Doc v2
Project Initialization and Research | Conduct Market Research and User Interviews, Create Project Documentation |  | This phase encompasses essential activities aimed at establishing a comprehensive understanding of project objectives, scope, and user needs. | 2024-01-05 | 2024-01-12
Subitems | Name | Owner | Status | Date
| Conduct Market Research and User Interviews |  | Working on it
| Create Project Documentation |  | Working on it
Design and Prototyping | Create Wireframes and Prototypes, Design User Interface and Experience |  | This phase involves crafting the user experience (UX) and user interface (UI) designs along with creating prototypes | 2024-01-15 | 2024-02-05
Subitems | Name | Owner | Status | Date
Create Wireframes and Prototypes
Design User Interface and Experience
Development | Backend Development, Frontend Development, Implement Basic SOS Functionality, Continuous Integration and Testing |  | This phase involves both frontend and backend development | 2024-01-15 | 2024-02-05
Subitems | Name | Owner | Status | Date
Backend Development
Frontend Development
Implement Basic SOS Functionality
Continuous Integration and Testing
Testing and Refinement | Quality Assurance Testing, Bug Fixes and Performance Optimization, User Acceptance Testing |  | This phase involves testing of functionalities, identifying and addressing any issues or discrepancies | 2024-02-05 | 2024-02-12
Subitems | Name | Owner | Status | Date
Quality Assurance Testing
Bug Fixes and Performance Optimization
User Acceptance Testing
Launch Preparation | Beta Testing, User Feedback Collection, Documentation for Launch |  | This phase involves finalizing the app for deployment, conducting beta tests with select user groups and necessary documentation | 2024-02-13 | 2024-02-16
Subitems | Name | Owner | Status | Date
Beta Testing
User Feedback Collection
Documentation for Launch
|  |  |  | 2024-01-05 | 2024-02-16
Version 2.0
Name | Subitems | Epic Owner | Description | Planned Timeline - Start | Planned Timeline - End | monday Doc v2
Feedback Analysis and Planning | Gather user feedback from Version 1.0, Conduct Surveys for Detailed Insights |  | This phase involves comprehensive feedback collection, data analysis, and planning again to enhance the app's functionalities | 2024-02-19 | 2024-02-23
Subitems | Name | Owner | Status | Date
Gather user feedback from Version 1.0
Conduct Surveys for Detailed Insights
Design and Development | User Interface (UI) Enhancements Based on Feedback, Implement Real-time Tracking Feature, Expand Emergency Contacts Functionality |  | This phase involves the app's user interface (UI) and user experience (UX) based on feedback analysis while integrating additional features to the app. | 2024-02-26 | 2024-03-15
Subitems | Name | Owner | Status | Date
User Interface (UI) Enhancements Based on Feedback
Implement Real-time Tracking Feature
Expand Emergency Contacts Functionality
Testing and Quality Assurance | Testing of New Features, Quality Assurance and Bug Fixing, User Acceptance Testing for New Functionalities |  | This phase involves comprehensive testing, bug fixing, and quality checks | 2024-03-16 | 2024-03-21
Subitems | Name | Owner | Status | Date
Testing of New Features
Quality Assurance and Bug Fixing
User Acceptance Testing for New Functionalities
Release Preparation | Beta Testing of Enhanced Features, App Store Submission Preparation, Documentation for Version 2.0 Release |  | This phase involves preparation, for releasing version 2 with new features | 2024-03-21 | 2024-03-22
Subitems | Name | Owner | Status | Date
Beta Testing of Enhanced Features
App Store Submission Preparation
Documentation for Version 2.0 Release
|  |  |  | 2024-02-19 | 2024-03-22
Version 3.0
Name | Subitems | Epic Owner | Description | Planned Timeline - Start | Planned Timeline - End | monday Doc v2
Performance Analysis and Planning | Analyze User Reviews and Feedback, Brainstorm and Ideate Innovative Functionalities |  | The phase aimed at evaluating Version 2.0's performance, analyzing user reviews, and planning innovative functionalities and enhancements for Version 3.0 of the app | 2024-03-22 | 2024-03-29
Subitems | Name | Owner | Status | Date
Analyze User Reviews and Feedback
Brainstorm and Ideate Innovative Functionalities
Advanced Feature Development | Develop AI-Driven Symptom Analysis, Implement Enhanced Security Measures |  | This phase involves the development of sophisticated features and integrations, leveraging emerging technologies to elevate the app's capabilities. | 2024-03-30 | 2024-04-14
Subitems | Name | Owner | Status | Date
Develop AI-Driven Symptom Analysis
Implement Enhanced Security Measures
Testing and Quality Assurance | Extensive Testing of Advanced Features, Security Audits and Fixes |  | This phase dedicated to ensuring the reliability, stability, and functionality of Version 3.0 of the app | 2024-04-15 | 2024-04-19
Subitems | Name | Owner | Status | Date
Extensive Testing of Advanced Features
Security Audits and Fixes
Version 3.0 Release | Official App Store Submission and Launch of Version 3.0 |  | This phase involves finalization of Version 3.0, including thorough testing, user feedback | 2024-04-22 | 2024-04-23
Subitems | Name | Owner | Status | Date
Official App Store Submission and Launch of Version 3.0
|  |  |  | 2024-03-22 | 2024-04-23